## Sheet1
Cost Baseline
|  | Task | Days | Total Cost
| Phase 1 | Feasibility | 35 | 70700
| 1.1 | Feasibility Study | 25 | 50000
| 1.1.1 | Risk Analysis | 25 | 10000
| 1.1.2 | Electric/Solar Load Analysis | 25 | 10000
| 1.2 | Owner Decision | 10
| 1.3 | License |  | 700
| Phase 2 | Planning & Design | 61 | 2460
| 2.1 | Statement of Work | 21 | 320
| 2.1.1 | General Requirements | 7 | 80
| 2.1.1.1 | Overhead | 2
| 2.1.1.2 | Fence | 1
| 2.1.1.3 | Roof (Patch) | 1
| 2.1.1.4 | Paint | 1
| 2.1.1.5 | Concrete | 2
| 2.1.2 | Structural Requirements | 7 | 80
| 2.1.2.1 | Materials | 3.5
| 2.1.2.2 | Labor | 3.5
| 2.1.3 | Electrical Requirements | 7 | 120
| 2.1.3.1 | Materials | 3
| 2.1.3.1.1 | Batteries | 2
| 2.1.3.1.2 | Solar Panels | 1
| 2.1.3.2 | Labor | 4 | 40
| 2.1.3.2.1 | Batteries | 2
| 2.1.3.2.2 | Solar Panels | 2
| 2.2 | Work Schedule & Cost Estimate | 10 | 120
| 2.2.1 | Work Schedule | 5 | 80
| 2.2.2 | Cost Estimate | 10 | 40
| 2.3 | RFQ (Bid) | 10 | 80
| 2.3.1 | Bid Analysis | 5 | 80
| 2.3.2 | Award Project | 10
| 2.4 | Contracting |  | 120
| 2.4.1 | Write Contract | 5 | 120
| 2.4.2 | Sign Contract | 5
| 2.5 | Submittals
| 2.5.1 | Single Line Drawing & Utility Site Plan | 5 | 160
| 2.5.2 | County Site Plan and Elevation Views | 5 | 120
| 2.6 | Electric Utility Approval | 15 | 800
| 2.6.1 | Electric Utility Approval - Rejected Submittal | 10 |  | New Requirements on inverters - Need to be UL-1741 SA compliant (Needs cutsheets and needs to be written explicitly on Single Line Drawing)
| 2.7 | County Permit | 10 | 700
| 2.8 | Procurement | 5 | 120
| 2.8.1 | Change in module purchase |  |  | (From step 3.1.2.1)
| Phase 3 | Construction/Building |  | 565000
| 3.1 | General Contractor | 35 | 92000
| 3.1.1 | Structural & Electrical | 20 | 113000
| 3.1.1.1 | Required Electric Utility Meter Tech is delayed | 5 |  | Due to the size of the system, the main breaker of the electrical panel must be de-rated. Here, the utility has to reschedule for 5 days later due to being overworked.
| 3.1.2 | Install Solar Panels, Inverters & Electrical Hook-up | 15 | 220000
| 3.1.2.1 | Solar Panels are delayed by 10 days | 10 |  | Owner does not receive extension of credit and must receive panels from another provider.
| 3.1.3 | Build Battery Shelter | 20 | 10000
| 3.1.4 | Install Batteries | 20 | 40000
| 3.1.5 | Install Transformers | 20 | 90000
| Phase 4 | Training | 6 | 15000
| 4.1 | O&M Batteries | 3 | 7500
| 4.2 | O&M Solar Panels | 3 | 7500
| Phase 5 | Turnover | 10 | 10000
| 5.1 | Review Acceptance Documents | 5 | 10000
| 5.1.1 | Accept As-Built Drawings | 5
| 5.2 | Owner Acceptance | 5
| 5.2.1 | Release Liens | 5
| 5.2.2 | Pay General Contractor | 5
|  | Total Cost |  | 663160

## Cost chart
Phase | Task | Days | Total Cost | 2.3 | RFQ (Bid) | 15 | 80 | Phase | Task | Days | Total Cost
Phase 1 | Feasibility | 35 | 70700 | 2.3.1 | Bid Analysis | 5 | 80 | Phase 1 | Feasibility | 35 | 70700
1.1 | Feasibility Study | 35 | 50000 | 2.3.2 | Award Project | 10 |  | Phase 2 | Planning & Design | 71 | 2540
1.1.1 | Risk Analysis | 35 | 10000 | 2.4 | Contracting | 6 | 120 | Phase 3 | Construction/Building | 50 | 565000
1.1.1.1 | Electric/Solar Load Analysis | 25 | 10000 | 2.4.1 | Write Contract | 5 | 120 | Phase 4 | Training | 6 | 15000
1.1.1.2 | Owner Decision | 10 |  | 2.4.2 | Sign Contract | 1 |  | Phase 5 | Turnover | 10 | 10000
1.2 | License |  | 700 | 2.5 | Submittals | 35 |  | Total |  | 172 | 663240
Phase 2 | Planning & Design | 120 | 2540 | 2.5.1 | Single Line Drawing & Utility Site Plan | 5 | 160
2.1 | Statement of Work | 49 | 320 | 2.5.2 | Electric Utility Approval | 10 | 800
2.1.1 | General Requirements | 37 | 80 | 2.5.3 | County Site Plan and Elevation Views | 5 | 120
2.1.1.1 | Overhead | 2 |  | 2.5.4 | County Permit | 10 | 700
2.1.1.2 | Fence | 1 |  | 2.5.5 | Procurement | 5 | 120
2.1.1.3 | Roof (Patch) | 6 |  | Phase 3 | Construction/Building | 40 | 565000
2.1.1.4 | Paint | 1 |  | 3.1 | General Contractor | 40 | 92000
2.1.1.5 | Concrete | 2 |  | 3.1.1 | Structural & Electrical | 20 | 113000
2.1.2 | Structural Requirements | 8 | 80 | 3.1.2 | Install Solar Panels, Inverters & Electrical Hook-up | 15 | 220000
2.1.2.1 | Materials | 4 |  | 3.1.3 | Build Battery Shelter | 20 | 10000
2.1.2.2 | Labor | 4 |  | 3.1.4 | Install Batteries | 20 | 40000
2.1.3 | Electrical Requirements | 4 | 120 | 3.1.5 | Install Transformers | 20 | 90000
2.1.3.1 | Materials | 2 |  | Phase 4 | Training | 6 | 15000
2.1.3.1.1 | Batteries | 2 |  | 4.1 | O&M Batteries | 3 | 7500
2.1.3.1.2 | Solar Panels | 1 |  | 4.2 | O&M Solar Panels | 3 | 7500
2.1.3.2 | Labor | 2 | 40 | Phase 5 | Turnover | 15 | 10000
2.1.3.2.1 | Batteries | 2 |  | 5.1 | Review Acceptance Documents | 5 | 10000
2.1.3.2.2 | Solar Panels | 2 |  | 5.1.1 | Accept As-Built Drawings | 5
2.2 | Work Schedule & Cost Estimate | 15 | 120 | 5.2 | Owner Acceptance | 10
2.2.1 | Work Schedule | 5 | 80 | 5.2.1 | Release Liens | 5
2.2.2 | Cost Estimate | 10 | 40 | 5.2.2 | Pay General Contractor | 5
|  |  |  | Total Cost |  |  | 663240